## Project schedule
Survey Outreach Effort
SurveyType | TASK | START | END | DURATION (workdays) | Target Outreach | Attempted Outreach | Outreach fail | Actual Outreach | Actual responses | Outreach Rate- KPI1 | Response Rate-KPI2 | Bulk Close | Bulk Close Rate-KPI3 | Phone Outreach Rate | Phone Completion Rate
Facility/Group | FAC&GRP_Jan2025 | 2025-01-06 | 2025-03-21 | 55 | 9827 | 9772 | 151 | 9621 | 5470 | 98.45% | 55.98% | 3769 | 68.9% | 35.15% | 31%
Facility/Group | Email Campaign | 2025-01-06 | 2025-01-17 | 10 | - | 7299 | 1182 | 6117 | 3979 | 83.81% | 54.51% | - | - | - | -
Facility/Group | Custom Emails | 2025-01-10 | 2025-01-10 | 1 | - | 290 | 0 | 290 | 69 | 100% | 23.79% | - | - | - | -
Facility/Group | Callogix_Effort | 2025-01-07 | 2025-02-19 | 32 | - | 3435 | 791 | 2644 | 1293 | 76.97% | 37.64% | - | - | - | -
Facility/Group | Letter Campaign | 2025-02-28 | 2025-03-21 | 16 | - | 791 | 151 | 640 | 129 | 80.91% | 16.31% | - | - | - | -
Facility/Group | Campaign Close |  | 2025-03-21
Dental | Dental_Mar2025 | 2025-03-04 | 2025-05-06 | 46 | 5282 | 4933 | 6 | 4927 | 2927 | 99.88% | 59.34% | 1835 | 62.69% | 34.97% | 73%
Dental | Email Campaign | 2025-03-04 | 2025-03-18 | 11 | - | 3920 | 1087 | 2833 | 1411 | 72.27% | 35.99% | - | - | - | -
Dental | Custom Emails | 2025-03-10 | 2025-03-10 | 1 | - | 377 | 0 | 377 | 377 | 100% | 100% | - | - | - | -
Dental | Dental Team Effort | 2025-03-05 | 2025-05-20 | 55 | - | 383 | 0 | 383 |  | 100% | 0% | - | - | - | -
Dental | Callogix_Effort | 2025-03-19 | 2025-04-07 | 14 | - | 1725 | 55 | 1670 | 1320 | 96.81% | 76.52% | - | - | - | -
Dental | Letter Campaign | 2025-04-07 | 2025-05-02 | 20 | - | 55 | 6 | 49 | 14 | 89.09% |  | -
Dental | Campaign Close |  | 2025-05-06
Facility/Group | FAC&GRP_Apr2025 | 2025-04-03 | 2025-06-09 | 48 | 9941 | 9886 | 122 | 9764 | 5533 | 98.77% | 55.97% | 4139 | 74.81% | 37.82% | 38%
Facility/Group | Email Campaign | 2025-04-02 | 2025-04-16 | 11 | - | 7296 | 1429 | 5867 | 4535 | 80.41% | 62.16% | - | - | - | -
Facility/Group | Custom Emails | 2025-04-07 | 2025-04-08 | 2 | - | 284 | 0 | 284 | 147 | 100% | 51.76% | - | - | - | -
Facility/Group | Callogix_Effort | 2025-04-08 | 2025-05-16 | 29 | - | 3739 | 532 | 3207 | 1667 | 85.77% | 44.58% | - | - | - | -
Facility/Group | Letter Campaign | 2025-05-19 | 2025-06-06 | 15 | - | 532 | 122 | 410 | 77 | 77.07% | 14.47% | - | - | - | -
Facility/Group | Campaign Close |  | 2025-06-09
Dental | Dental_Jun2025 | 2025-06-02 | 2025-08-04 | 46 | 5253 | 4922 | 26 | 4896 | 2926 | 99.47% | 59.45% |  | 75% | - | 45%
Dental | Email Campaign | 2025-06-02 | 2025-06-16 | 11 | - | 3953 |  | 3953 | 2264 | 100% | 57.27% | -
Dental | Custom Emails | 2025-06-03 | 2025-06-04 | 2 | - | 353 | 0 | 353 | 169 | 100% | 47.88% | -
Dental | Dental Team Effort | 2025-06-02 | 2025-08-04 | 46 | - | 331 |  | 331 |  | 100% | 0% | -
Dental | Callogix_Effort | - | - | - | - | - | - | - | - | - | - | -
Dental | Letter Campaign | 2025-06-30 | 2025-08-01 | 25 | - | 616 | 26 | 590 | 417 | 95.78% | 70.68% | -
Dental | Campaign Close |  | 2025-08-04
Facility/Group | FAC&GRP_Aug2025 | 2025-08-20 | 2025-11-17 | 64 | 10154 | 10099 |  | 10099 | 5624 | 100% | 55.69% |  | 77% | 30.7% | 37%
Facility/Group | Email Campaign | 2025-08-20 | 2025-09-03 | 11 |  | 7389 | 1163 | 6226 | 3940 | 84.26% | 53.32%
Facility/Group | Custom Emails | 2025-09-08 | 2025-09-08 | 1 | - | 281 | 0 | 281 | 178 | 100% | 63.35%
Facility/Group | Callogix_Effort | 2025-09-10 | 2025-10-23 | 32 |  | 3100 | 426 | 2674 | 1395 | 86.26% | 45%
Facility/Group | UB Email Campaign | 2025-10-06 | 2025-10-06 | 1 |  | 1046 | 741 | 305 | 93 | 29.16% | 8.891%
Facility/Group | Group Email Campaign | 2025-10-17 | 2025-10-17 | 1 |  | 568 | 16 | 552 | 248 | 97.18% | 43.66%
Facility/Group | Letter Campaign | 2025-10-24 | 2025-11-14 | 16 |  | 426 |  | 426 | 72 | 100% | 16.9%
Facility/Group | Campaign Close |  | 2025-11-17
Dental | Dental_Oct2025 | 2025-10-01 | 2025-12-08 | 49 | 5156 | 4889 |  | 4889 | 2293 | 100% | 46.9% |  | 75% | 12.07% | 33%
Dental | Email Campaign | 2025-10-01 | 2025-10-15 | 11 | - | 4248 | 897 | 3351 | 2007 | 78.88% | 47.25% | -
Dental | Custom Emails | 2025-10-03 | 2025-10-03 | 1 | - | 376 | 0 | 376 | 115 | 100% | 30.59% | -
Dental | Dental Team Effort | 2025-10-01 | 2025-12-01 | 44 | - | 267 |  | 267 |  | 100% | 0% | -
Dental | Callogix_Effort | 2025-10-24 | 2025-11-14 | 16 | - | 590 | 45 | 545 | 402 | 92.37% | 68.14% | -
Dental | Group Email Campaign | 2025-11-05 | 2025-11-05 | 1 | - | 719 | 15 | 704 | 222 | 97.91% | 30.88%
Dental | Letter Campaign | 2025-11-17 | 2025-12-05 | 15 | - | 39 |  | 39 | 6 | 100% | 15.38% | -
Dental | Campaign Close |  | 2025-12-08
Facility/Group | FAC&GRP_Nov2025 (December) | 2025-12-03 | 2026-01-09 | 28 | 10065 | 10012 |  | 10012 | 4959 | 100% | 49.53% |  | 76% | 26.92% | 42%
Facility/Group | Email Campaign | 2025-12-03 | 2025-12-17 | 11 | - | 7727 | 1283 | 6444 | 3548 | 83.4% | 45.92%
Facility/Group | Custom Emails | 2025-12-05 | 2025-12-05 | 1 | - | 293 | 0 | 293 | 172 | 100% | 58.7%
Facility/Group | Callogix_Effort | 2025-12-03 | 2026-01-09 | 28 | - | 2695 | 367 | 2328 | 1163 | 86.38% | 43.15%
Facility/Group | Group Email Campaign | 2025-12-17 | 2025-12-17 | 1 | - | 940 | 56 | 884 | 308 | 94.04% | 32.77%
Facility/Group | Letter Campaign | - | - | - | - | - | - | - | - | - | -
Facility/Group | Campaign Close |  | 2026-01-09

## Definition
Term | Description | Details on Derivations
Target Outreach | Target outreach is ideally every survey that has been systemically identified so in 2025 onwards we would like to report the number of records generated in the systemically generated seed file or the survey input file. Calendar year 2024 however we were counting the number of records present in the actual loaded seed file or the survey input file loaded by the business team after excluding the bad data however going forward as per nancy's suggestion we would like to keep a close eye on any bad data that has been dropped because of various reasons like genuinely bad data multiple Billings windows are open inventory | # of records from seed file or survey inut file from folder: Systemgenerated
Attempted Outreach | Target outreach minus bad data (data dropped by business team intentionally) | # of records from seed file or survey inut file from folder: PO Generated
Outreach fail | Number of surveys for which we could not reach out to the corresponding person Please note this number should only reflect those providers to whom we cannot outreach at all through any of this following channels emails or through call logics or through letters for example if car logics could not reach out but we were able to send a letter then it is considered outreach success | equals the outreach fail for the last channel used to outreach(usually letters??)
Outreach fail (Callogix) | Number of surveys for which Callogix was unable to reach out to the corresponding person. | equals # of No voicemail option + Phone not in service/wrong number + select Other outcomes on Callogix NUB list
Actual Outreach | Actual Outreach | equals Attempted Outreach minus Outreach fail
Actual responses | Actual responses
Outreach Rate- KPI1 | Actual Outreach/Target Outreach
Response Rate-KPI2 | Actual Responses/Actual Outreach
Bulk Close | # of surveys eligible for bulk closure. Until R48 goes live this can be derived from Kirk's file | Refert o latest response file for any given campaign - Fro example P:\PCA\Directory Team\CAA_90DaySurveys\Professional\Professional_Nov2024\POGenerated\BulkInventoryAnalysis
Bulk Close Rate-KPI3 | Bulk Close/Actual responses
callogix outreach rate | Rate of outreach being worked by callogix each campaign. | callogix effort/attempted outreach
Callogix Completion Rate | Rate of responses gathered from Callogix outreach. | Response file compared against Callogix effort
Cost | Based on March 2024 statement we understand callogix staffs 0.13 hour per call and charges $27.5/hr. Hence cost per call is Callogix had (5988 outbound with average of 1:43 and 286 inbound calls with 4:02 average time) Cost per call =$3.58 and cost per letter = $1.25 | Outreach by calls*3.58+outreach by letters*1.25

## 2024Visual
Provider Directory Validation for 2024Q1
Survey_Type | Initial Identified Outreach | Target Outreach | Outreach fail | Actual Outreach | Actual responses | Bulk Close | Outreach Rate- KPI1 | Response Rate-KPI2 | Bulk Close Rate-KPI3 | Cost
Facility_Group |  | 8564 | 444 | 8120 | 4047 | 2661 | 94.82% | 49.84% | 65.75% | 22558.17
Medical |  | 4975 | 857 | 4775 | 1635 | 355 | 95.98% | 34.24% | 21.71% | 9538.24
dental |  | 4792 | 455 | 4592 | 3346 | 2371 | 95.83% | 72.87% | 70.86% | 9736.7
41833.11
Provider Directory Validation for 2024Q2
Add hyperlink link for known limitations
Survey_Type | Initial Identified Outreach | Target Outreach | Outreach fail | Actual Outreach | Actual responses | Bulk Close | Outreach Rate- KPI1 | Response Rate-KPI2 | Bulk Close Rate-KPI3 | Cost
Facility_Group_Apr | 9407 | 9362 |  | 9362 | 6032 | 4494 | 100% | 64.43% | 74.5% | 31164.41
Medical_May | 9011 | 7490 | 139 | 7351 | 2250 | 658 | 98.14% | 30.61% | 29.24% | 25979.75
dental_June | 5151 | 4837 | 0 | 4837 | 2247 | 1735 | 100% | 46.45% | 77.21% | 4203.34
61347.5
Provider Directory Validation for 2024Q3
Add hyperlink link for known limitations
Survey_Type | Initial Identified Outreach | Target Outreach | Outreach fail | Actual Outreach | Actual responses | Bulk Close | Outreach Rate- KPI1 | Response Rate-KPI2 | Bulk Close Rate-KPI3 | Cost
Facility_Group_Jul |  | 9434 |  |  | 4986 |  | 0% | 52.85% | 0%
Medical_Aug |  | 8115 |  |  | 1582 |  | 0% | 19.49% | 0%
dental_Sep |  | 4978 |  |  | 2868 |  | 0% | 57.61% | 0%